*Monitoring indicators September 2022*

|  |  |  |
| --- | --- | --- |
| **Theme** | **Indicator** | **Update September 2022** |
| *Habitat restoration* | Number of ha restored in Portofino  | 2.282 |
| Number of ha restored in Parco Po | 19 |
| *Orchid population reinforcement* | Number of OMRs in which outplanting has taken place Portofino | 1: Gave |
| Seedlings outplanted (by species) Portofino | *Ophrys bertolonii* 2 |
|  | Number of OMRs in which outplanting has taken place (Po) | 2: Bric Montariolo, Basso Scrivia |
|  | Seedlings outplanted (by species) in Parco Po | *Serapias neglecta* 8*Anacamptis morio* 8*Himantoglossum adriaticum* 2 *Himantoglossum robertianum* 1 |
| *Land Stewardship* | LS Agreements signed | 93 |
| Area covered by LSAs (ha) | 118 |
| *Networking* | International networking meetings | 3 |
| People participating in networking  | Approx. 70 |
| *Training*  | Number of training events | 46 |
| People participating in training events | Approx. 1500 (n. presences) |
| *Dissemination* | People participating in orchid festivals/events | Approx. 485 |
| Website  | Users: 6881Sessions: 9760Pageviews: 19677 |
| Social media  | Twitter: 144 followers Instagram: 603 followers FB: 2282 followers |
|  |

|  |
| --- |
| Displayed information (poster, information boards) 10 |
| Events/exhibitions 13 |
| Publications/reports 1 |
| Print media 18 |
| Other media (video/broadcast) 35 |

 |

*Monitoring indicators March 2022*

|  |  |  |
| --- | --- | --- |
| **Theme** | **Indicator** | **Update March 2022** |
| *Habitat restoration* | Number of ha restored in Portofino  | 2.282 |
| Number of ha restored in Parco Po | 15 |
| *Orchid population reinforcement* | Number of OMRs in which outplanting has taken place Portofino | 1: Gave |
| Seedlings outplanted (by species) Portofino | *Ophrys bertolonii* 2 |
|  | Number of OMRs in which outplanting has taken place (Po) | 2: Bric Montariolo, Basso Scrivia |
|  | Seedlings outplanted (by species) in Parco Po | *Serapias neglecta* 8*Anacamptis morio* 8*Himantoglossum adriaticum* 2 *Himantoglossum robertianum* 1 |
| *Land Stewardship* | LS Agreements signed | 76 |
| Area covered by LSAs (ha) | 114 |
| *Networking* | International networking meetings | 3 |
| People participating in networking  | Approx. 70 |
| *Training*  | Number of training events | 41 |
| People participating in training events | Approx. 1350 (n. presences) |
| *Dissemination* | People participating in orchid festivals/events | Approx. 370 |
| Website  | Users: 5351Sessions: 7724Pageviews: 15880 |
| Social media  | Twitter: 140 followers Instagram: 533 followers FB: 2114 followers |
|  |

|  |
| --- |
| Displayed information (poster, information boards) 10 |
| Events/exhibitions 10 |
| Publications/reports 1 |
| Print media 18 |
| Other media (video/broadcast) 33 |

 |

*Monitoring indicators September 2021*

|  |  |  |
| --- | --- | --- |
| **Theme** | **Indicator** | **Update September 2021**  |
| *Habitat restoration* | Number of ha restored in Portofino  | 1.282 |
| Number of ha restored in Parco Po | 15 |
| *Orchid population reinforcement* | Number of OMRs in which outplanting has taken place Portofino | 0 |
| Seedlings outplanted (by species) Portofino | 0 |
|  | Number of OMRs in which outplanting has taken place (Po) | 1 |
|  | Seedlings outplanted (by species) in Parco Po | *Serapias neglecta* 6*Anacamptis morio* 3*Himantoglossum adriaticum* 2 *Himantoglossum robertianum* 1 |
| *Land Stewardship* | LS Agreements signed | 72 |
| Area covered by LSAs (ha) | 112 |
| *Networking* | International networking meetings | 3 |
| People participating in networking  | Approx. 70 |
| *Training*  | Number of training events | 28 |
| People participating in training events | Approx. 660 |
| *Dissemination* | People participating in orchid festivals/events | Approx. 320 |
| Website  | Users: 4006Sessions: 5755Pageviews: 12158 |
| Social media  | Twitter: 138 followersInstagram: 463 followers FB: 1603 followers |
|  |

|  |
| --- |
| Displayed information (poster, information boards) 10 |
| Events/exhibitions 9 |
| Publications/reports 1 |
| Print media 18 |
| Other media (video/broadcast) 13 |

 |

*Monitoring indicators February 2021*

|  |  |  |
| --- | --- | --- |
| **Theme** | **Indicator** | **Update February 2021**  |
| *Habitat restoration* | Number of ha restored in Portofino  | 0.838 |
| Number of ha restored in Parco Po | 6 |
| *Orchid population reinforcement* | Number of OMRs in which outplanting has taken place Portofino |  |
| Seedlings outplanted (by species) Portofino | 0 |
|  | Number of OMRs in which outplanting has taken place (Po) | 1 |
|  | Seedlings outplanted (by species) in Parco Po | *Serapias neglecta* 6 *Anacamptis morio* 3*Himantoglossum adriaticum* 2 *Himantoglossum robertianum* 1 |
| *Land Stewardship* | LS Agreements signed | 32 |
| Area covered by LSAs (ha) | 55 |
| *Networking* | International networking meetings | 2 |
| People participating in networking  | Approx. 40 |
| *Training*  | Number of training events | 10 |
| People participating in training events | Approx. 380  |
| *Dissemination* | People participating in orchid festivals/events | Approx. 320 |
| Website  | Users: 2931Sessions: 4210Pageviews: 7953 |
| Social media  | Twitter: 128 followersInstagram: 358 followers FB: 1315 followers |
| Other tools |

|  |
| --- |
| Displayed information (poster, information boards) 10 |
| Events/exhibitions 8 |
| Publications/reports 1 |
| Print media 14 |
| Other media (video/broadcast) 10 |

 |